## Plan
IronCalc v1.0 · PROJECT PLAN
Read-only sheet. Edit data in 'Tasks' and 'Settings' | [7 empty] | 2026-10-10 | [21 empty] | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01
# | Phase | Task | Owner | Start Date | Days | End Date | % Done | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06
added by SharpCell
1 | Planning | Define scope & goals | John | 2026-10-10 | 4 | 2026-10-14 | 50%
2 | Planning | Stakeholder interviews | John | 2026-10-14 | 3 | 2026-10-17 | 20%
3 | Planning | Requirements doc | John | 2026-10-17 | 5 | 2026-10-22 | 80%
4 | Planning | Tech stack decision | Jane | 2026-10-22 | 3 | 2026-10-25 | 60%
5 | Design | UX wireframes | Jane | 2026-10-25 | 6 | 2026-10-31 | 10%
6 | Design | Design system / tokens | Jane | 2026-10-31 | 5 | 2026-11-05 | 20%
7 | Design | Prototype review | John | 2026-11-05 | 3 | 2026-11-08 | 0%
8 | Dev | Spreadsheet engine core | Jane | 2026-11-08 | 8 | 2026-11-16 | 0%
9 | Dev | Formula parser v2 | Jane | 2026-11-16 | 2 | 2026-11-18 | 0%
10 | Dev | Frontend components | John | 2026-11-18 | 3 | 2026-11-21 | 0%
11 | Dev | WebAssembly build | John | 2026-11-21 | 8 | 2026-11-29 | 0%
12 | Dev | API integration | Jane | 2026-11-29 | 10 | 2026-12-09 | 0%
13 | Testing | Unit test suite | John | 2026-12-09 | 6 | 2026-12-15 | 0%
14 | Testing | Cross-browser QA | Jane | 2026-12-15 | 5 | 2026-12-20 | 0%
15 | Testing | Performance benchmarks | Jane | 2026-12-20 | 5 | 2026-12-25 | 0%
16 | Testing | Bug fixes | John | 2026-12-25 | 5 | 2026-12-30 | 0%
17 | Launch | Docs & changelog | John | 2026-12-30 | 4 | 2027-01-03 | 0%
18 | Launch | Beta release | Jane | 2027-01-03 | 3 | 2027-01-06 | 0%
19 | Launch | Marketing page | Jane | 2027-01-06 | 5 | 2027-01-11 | 0%
20 | Launch | v1.0 release 🚀 | John | 2027-01-11 | 2 | 2027-01-13 | 0%

## Tasks
TASK INPUT
Edit here (plan updates automatically)
# | Phase | Task Name | Owner | Start Date | Days | End Date | % Done | Notes
1 | Planning | Define scope & goals | John | 2026-10-10 | 4 | 2026-10-14 | 50%
2 | Planning | Stakeholder interviews | John | 2026-10-14 | 3 | 2026-10-17 | 20%
3 | Planning | Requirements doc | John | 2026-10-17 | 5 | 2026-10-22 | 80%
4 | Planning | Tech stack decision | Jane | 2026-10-22 | 3 | 2026-10-25 | 60%
5 | Design | UX wireframes | Jane | 2026-10-25 | 6 | 2026-10-31 | 10%
6 | Design | Design system / tokens | Jane | 2026-10-31 | 5 | 2026-11-05 | 20%
7 | Design | Prototype review | John | 2026-11-05 | 3 | 2026-11-08 | 0%
8 | Dev | Spreadsheet engine core | Jane | 2026-11-08 | 8 | 2026-11-16 | 0%
9 | Dev | Formula parser v2 | Jane | 2026-11-16 | 2 | 2026-11-18 | 0%
10 | Dev | Frontend components | John | 2026-11-18 | 3 | 2026-11-21 | 0%
11 | Dev | WebAssembly build | John | 2026-11-21 | 8 | 2026-11-29 | 0%
12 | Dev | API integration | Jane | 2026-11-29 | 10 | 2026-12-09 | 0%
13 | Testing | Unit test suite | John | 2026-12-09 | 6 | 2026-12-15 | 0%
14 | Testing | Cross-browser QA | Jane | 2026-12-15 | 5 | 2026-12-20 | 0%
15 | Testing | Performance benchmarks | Jane | 2026-12-20 | 5 | 2026-12-25 | 0%
16 | Testing | Bug fixes | John | 2026-12-25 | 5 | 2026-12-30 | 0%
17 | Launch | Docs & changelog | John | 2026-12-30 | 4 | 2027-01-03 | 0%
18 | Launch | Beta release | Jane | 2027-01-03 | 3 | 2027-01-06 | 0%
19 | Launch | Marketing page | Jane | 2027-01-06 | 5 | 2027-01-11 | 0%
20 | Launch | v1.0 release 🚀 | John | 2027-01-11 | 2 | 2027-01-13 | 0%
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Formulas:
Start Date = [End Date, row above]
End Date = [Start Date]+[Days]

## Settings
PROJECT SETTINGS
Project Name | IronCalc v1.0 | Name shown on the Plan header
Project Start | 2026-10-10 | First date shown on the Gantt timeline
Days to show | 120 | Number of calendar days in the Gantt (max ~120)
Today | 2026-10-10 | Auto, do not edit
Owner 1 | John
Owner 2 | Jane
Owner 3
Owner 4
Phase colours (reference)
Planning
Design
Dev
Testing
Launch
Other

## METADATA (hidden)
NOW | 46305.999

## SharpCell
207 | 1234.5
1
2
3